## Sheet1
Date | Name | Description | Candidate Planning | Candidate Execution | Registered BSA Youth | Other Youth | Registered BSA Adult | Other Adult | Overall
|  | Total hours | 34.25 | 9 | 8 | 16 | 20.25 | 16 | 103.5
2020-11-01 | Me | Brainstorm & Decide on Project | 2
2020-11-01 | SM Jones | Brainstorm & Decide on Project |  |  |  |  | 2
2020-11-01 | dad | Brainstorm & Decide on Project | [5 empty] | 2
2020-11-01 | mom | Brainstorm & Decide on Project | [5 empty] | 2
2020-11-01 | Ms. Smith, Eagle Coach | Brainstorm & Decide on Project |  |  |  |  | 2
2020-11-02 | Me | Discuss with Beneficiary | 2
2020-11-02 | Ms. Beneficiary | Discuss with Beneficiary | [5 empty] | 2
2020-11-02 | Mom | Discuss with Beneficiary | [5 empty] | 2
2020-11-03 | Me | Write up Proposal in Workbook | 1.5
2020-11-03 | Me | Write up Proposal in Workbook | 1
2020-11-03 | Me | Write up Proposal in Workbook | 0.5
2020-11-03 | Me | Complete Fundraising Application | 0.5
2020-11-04 | Me | Review/Edit Proposal | 2
2020-11-04 | Ms Smith, Eagle Coach | Review/Edit Proposal |  |  |  |  | 2
2020-11-05 | Me | Review Proposal and sign | 2
2020-11-05 | SM Jones | Review Proposal and sign |  |  |  |  | 2
2020-11-06 | Me | Review Proposal and sign | 2
2020-11-06 | CC Johanson | Review Proposal and sign |  |  |  |  | 2
2020-11-07 | Me | Review Proposal and sign | 2
2020-11-07 | Ms. Beneficiary | Review Proposal and sign | [5 empty] | 2
2020-11-08 | Me | Submit Proposal to District | 0.5
2020-11-09 | Me | Getting Proposal approval | 0.25
2020-11-09 | District Rep | Getting Proposal approval |  |  |  |  | 0.25
2020-11-10 | Me | Review Project | 2
2020-11-10 | Ms Smith, Eagle Coach | Review Project |  |  |  |  | 2
2020-11-11 | Me | Write up Plan in Workbook | 6
2020-11-12 | Me | Review Plan | 2
2020-11-12 | Ms Smith, Eagle Coach | Review Plan |  |  |  |  | 2
2020-11-13 | Youth1 | Plan Fundraising |  |  |  | 4
2020-11-14 | Youth2 | Conduct Fundraising |  |  |  | 4
2020-11-15 | Me | Schedule and publish work date(s)
2020-11-16 | Me | Project Work day |  | 9
2020-11-16 | Scout1 | Project Work day |  |  | 4
2020-11-16 | Scout2 | Project Work day |  |  | 4
2020-11-16 | Youth1 | Project Work day |  |  |  | 4
2020-11-16 | Youth2 | Project Work day |  |  |  | 4
2020-11-16 | Adult1 | Conduct Fundraising |  |  |  |  | 4
2020-11-16 | Adult4 | Conduct Fundraising | [5 empty] | 4
2020-11-17 | Me | Write up Project Report | 4
2020-11-18 | Me | Review Report and sign | 2
2020-11-18 | Ms. Beneficiary | Review Report and sign | [5 empty] | 2
2020-11-19 | Me | Review Report and sign | 2
2020-11-19 | SM Jones | Review Report and sign |  |  |  |  | 2
Formulas:
Date = [Date, row above]